## Highlevel Plan
Objective | Diversly Adaptable Modular Robot for weed detection in Agricultural setup
Abstract | Food production is highly diverse in several aspects. Even farms that grow the same crops may differ in topology, infrastructure, production method, and so on. Modular robots help us adapt to this diversity, as they can quickly be configured for various farm environments. The robots proposed in this work are hardware modular in the sense that they can be reconfigured to obtain the necessary physical properties to operate in different production systems—such as tunnels, greenhouses and open fields—and their mechanical properties can be adapted to adjust for track width, power requirements, ground clearance, load capacity, and so on. The robot’s software is generalizing to work with the great variation of robot designs that can be realized by assembling hardware modules in different configurations
Git Hub Page for The Project:
Week | Intern-1 | Intern-2 | Intern-3 | Intern-4 | Expected Deliverable
Week 1 | Literature Survey | Literature Survey | Literature Survey | Literature Survey | 1. The students will prepare a detailed Report on their findings in their respective Modules 2. Set up their working environment, install packages 3. Get their hands on with The tools and learn techniques and tools that are required for The said job 4. Try to impliment a few simple ideas in The available literature
Week 2 | Module Design: Robot Frame 1. Design a few Robot Frames that are modular 2. Validate the design against a few exsisting frames | 1. Identify the Sensors and Actuators 2. Developing Data Acquisition sensor circuits 3. Building Actuator logic into the board for seering the robot | Setting up Simulation for the controlling the Robot movements | Idetifying exsisiting designs that can be simulated. Setting up Simulation environment and conducting simulaton activities | 1. Robot Frame Design and Validation 2. Setting up sensor circuits 3. Simulation of Robot Movement in predefined terrain
Week 3 | Module Design: 1. Drive Module Depending on the torque and weight requirements of the robot 2. Validating the drive Module using simulations for various terrain 3. Integrating Drive and Robot Frame | 1. Connecting Camera Module 2. Developing image acquisition, processing and Storage | 1. Integration of Drive module wit the simulation 2. Validating the results of the simulation with the physical movement 3. Developing a Basic Motor Controller using ROS | Exploring and Building MI networks for weed dectection Identifying the dataset / Data curation | 1. A Manuevring Robot that matches its movements with the simulation 2. A camera Module that can capture, process and store the aquired data
Week 4 | Defining Various Modifyable Configurations Enabling Physical control of these configuarations | Development of image processing algorithms for Processing object detection in a farm environment | integrating Robot Controller of the ROS to the drive module of the robot | Building the MI model and validating the model. Field testing the model for its accuracy | 1. ROS integrated manverable robot 2. Data Acquision and data processing module
Week 5
Week 6

## Work-Break-Down
Date | Name | H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11 | H12
2021-09-13 | KP | H1: Literature Survey - 10 Papers
| BRH | H1: Literature Survey - 10 Papers
| YNV | H1: Literature Survey - 10 Papers
2021-09-14 | KP
BRH
YNV
2021-09-15 | KP
BRH
YNV
2021-09-16 | KP
BRH
YNV
2021-09-17 | KP
BRH
YNV